## Sheet1
| 纠正预防措施报告 |  |  | 状态 |  | 小组组长 | 科长 |  | 经理
| 起始日期： |  |  | 开启 | 关闭
结束日期：
(1)成立小组 |  | (2) 问题描述 |  | 零部件编号：
联系人： |  | 车系: |  | 零部件名称：
电话： |  | 反馈人: |  | 问题发生地点:
邮箱： |  | 问题描述:
小组成员
(3) 临时措施 |  |  | 责任人 | 计划完成 | 实际完成 | 验证
|  |  |  | 时间 | 时间 | 验证方法 |  | 验证结果
(4) 根本原因 | 问题发生的原因: |  | 问题流出的原因:
(5) 根本措施 |  |  | 责任人 | 计划完成 | 实际完成 | (6) 效果验证
|  |  |  | 时间 | 时间 | 验证方法 |  | 验证结果
(7) 预防再发生 |  |  | 责任人 | 计划完成 | 实际完成
|  |  |  | 时间 | 时间
(8) 小组总结

## 案例
|  | Rev-08/99 | Corrective Action Report (CAR) |  |  |  | Status: |  | Customer QR / Concern#'s | CAR/QCR #
|  | Supp City/St | Date Opened: | 2002-03-06 | Next Status Due Date: |  | Open / Closed |  |  | Division #
|  | Supp Cd | Date Revised: | 2002-03-07 | Close Date: |  |  |  |  | Supplier #
(1) TEAM CONTACT |  |  |  | (2) PROBLEM DESCRIPTION |  |  | Component Part No.:
Contact | Name |  |  | Car Model: | Light Truck |  | Lear Part No. / Descri.:
Phone |  |  |  | Initiator: |  |  | Location: |  | City, State
Activity |  |  |  | Problem Description:
Team Members
On 3/6/02, xxxx of xxxx, was notified by xxxx of Ford Kansas City that there was a mislabeling concern on part number xxxx. XXXX informed xxxx that we had shipped 820 pieces under packing slip #0132258. 779 pieces were actually part # yyyy.
(3) CONTAINMENT ACTIONS | [5 empty] | Responsible | TARGET | EFFECTIVE | VERIFICATION
ACTION(S): | [5 empty] | Person | DATE | DATE | METHODS | RESULTS
All Stock at xxxx was immediately rejected, quarantined, and 100% visually inspected. We 100% inspected 779 pieces of part number xxxx and charted a plane to deliver the parts to Kansas City. The 779 certified parts arrived at Kansas City at 4:00 p.m. Another 984 pcs. were expedited by truck on 3/6/02 to cover the suspect stock in transit. The rest of the stock at xxxx was also 100% inspected: 2,460 pcs. of part number xxxx and 2,460 pieces of part number yyyy. There were 0 boxes found in house that were mislabeled. Also, xxxx QRE, xxxx, 100% inspected the rest of the inventory at Kansas City. She inspected 5,250 pcs. of part number xxxx and 2,100 pcs. of yyyy. There were 0 boxes mislabeled. | [6 empty] | 2002-03-07 | 2002-03-07 | Each container was opened and the parts were verified to be the correct part number. Each container was verified (visually) that the correct parts were labeled with the correct bar-code label. | A total of 5,699 pcs. of both part numbers were 100% inspected at xxxx with 0 pieces found defective. Also, 7,350 pcs. have been inspected at Kansas City with 0 pcs. found defective since the reject.
(4) ROOT CAUSES |  |  | CAUSE(S) FOR OCCURRENCE: |  |  | CAUSE(S) FOR ESCAPE:
The operator at the end of the assembly line placed the incorrect labels on the containers because the operators had access to both labels (part numbers xxxx & yyyy). The production line made a change over from the L/H part to the R/H part. However, the person that was placing the parts in the container and putting the bar-code labels on the boxes did not change out the labels. The defect occurred on 3/1/02. | [5 empty] | Our inspection and final audit procedures are not full proof. The packaging and verification activities for this assembly line are still controlled by humans which are subject to mistakes. Our current inspection instructions call for the first box of parts to be compared to the bar-code label as a first pc. inspection. However, there are no hourly checks or last-off comparisons in the inspection instructions which would have the operator, periodically, verify the correct parts to the correct label.
(5) CORRECTIVE ACTIONS | [5 empty] | Responsible | TARGET | EFFECTIVE | (6) VERIFICATION
Interim Actions: | [5 empty] | Person | DATE | DATE | METHODS | RESULTS
Until further notice, the operators will place parts in the containers. They will not tape the lid shut. They will place the boxes on the floor near the assembly line. Then, a Senior Facilitator will come by, inspect the box of parts and ensure that the correct labels are at the work station. After the Facilitator verifies that the correct parts are matched with the correct labels, she will tape the box shut and apply the bar-code label. This interim procedure began on 3/6/02. Each container will have a Green "X" to signify certification. | [6 empty] | 2002-03-06 | 2002-03-06 | This will be a visual inspection by the operators then another visual inspection by the Facilitators. Process began 3/6/02. | Since the implementation of this interim process, we have ran 12,000 pcs. of both part numbers without any further concerns.
Permanent Actions:
Ensure that the operators who are placing the bar-codes on the boxes do not have access to both part number labels. There will be no bar-code labels held at the assembly line. When an order needs to be processed, the Facilitator will have shipping generate the number of labels needed to cover that specific order. No excess labels will be generated. If, when an order is completed, there are labels left over, they will be removed from the assembly line and taken back to shipping. | [6 empty] | 2002-03-06 | 2002-03-06 | The Facilitator will have the labels generated from shipping for both part numbers by order. Only the bar-codes needed for a specific order will be generated. No extra labels will be made. | Since the implementation of this interim process, we have ran 12,000 pcs. of both part numbers without any further concerns.
(7) PREVENTION | [5 empty] | Responsible | TARGET | EFFECTIVE | (6) VERIFICATION
Preventative Measures: | [5 empty] | Person | DATE | DATE | METHODS | RESULTS
1. Add description line to Bar-Code label that distinguishes R/H and L/H part. The Bar-Code Label will contain the description "LEFT HAND" for part number xxxx and "RIGHT HAND" for part number yyyy 2. Label the100% Checking Fixtures with the part numbers and a drawing of the part showing the correct part and correct label. 3. Add inspection check that would require operators to verify the parts and labels every hour during production. This would be in addition to the First Pc. Approval and the Final Audit. | [6 empty] | 2002-04-08 |  | Pending | Pending
(8) TEAM MEMBER / REVIEW & APPROVALS
Team Champion: |  |  |  |  | Quality Manager: | Terry Melton |  | Plant Manager: |  | Ernie Baker
Review & Approval Date: |  |  |  |  | Review and Approval Date: |  |  | Review and Approval Date: